## Sheet1
Task | Duration | Start Month | End Month | Description | Year Count
Literature Review & Dataset Collection | 2 | 0 | 2 | Research existing techniques in emotion detection, pose estimation, and doubles tennis. Collect publicly available datasets and/or annotate custom datasets. | Year 1
Facial Feature Extraction (ResNet50) | 3 | 2 | 5 | Develop and test ResNet50 for facial feature extraction from detected faces.
Body & Facial Expression recognition | 4 | 5 | 9 | Evaluate accuracy of body and facial expression detection on sample datasets.
Emotion Mapping Model Development | 5 | 9 | 14 | Develop a neural network model to classify emotional states based on body and facial features. | Year 2
Multimodal Integration (Body + Face) | 2 | 14 | 16 | Integrate body posture and facial expressions in a multimodal framework for emotion recognition.
Synchronization (DTW) Implementation | 2 | 16 | 18 | Implement Dynamic Time Warping (DTW) to calculate synchronization between players' movements.
Interaction Quality Evaluation | 4 | 18 | 22 | Implement interaction detection module to evaluate non-verbal interactions like high-fives, pointing, etc. | Year 3
Development of Chemistry Score | 6 | 22 | 28 | Develop a formula to compute team chemistry based on synchronization, emotional congruence, and interaction quality.
Event Detection Model (SlowFast) | 3 | 28 | 31 | Implement SlowFast-based deep learning model to detect match events like rallies, aces, breakpoints, etc.
Event-Emotion Correlation Analysis | 2 | 31 | 33 | Develop an algorithm to correlate detected events with players’ emotions and chemistry scores.
Dashboard Development | 2 | 33 | 35 | Design and implement a dashboard to visualize match events, emotional states, and chemistry dynamics.
System Integration & Final Testing | 1 | 35 | 36 | Perform final integration of all system components and validate on full-length tennis matches.